## Sheet1
| Sunday | Monday | Tuesday | Wednesday | Thursday | Friday
Zhongqiu Gao | Angular project creation | 1. Auth server 1. register/login backend | 5. Hire(front end + backend) | 5. Visa Status Management frontend | 5. Visa Status Management backend | Bug fixing
Yaocheng Tong |  | 3. Employee Homepage frontend 2. Onboarding frontend | 6. House Management(frontend + backend) | 2. Onboarding backend | 6. Housing (backend) | Bug fixing
Bailey Bai | Domain/entities creation in spring boot project | 1. Normal user Login/Registration frontend 1. HR Login frontend 3. Employee Profile(back end) | 4. Employee Personal Information frontend | 4. Visa Status Management(frontend + backend) | Employee frontend styling HR frontend styling | Bug fixing
Shida Sheng |  | 3. Employee Homepage backend 3. Employee Profile(frontend) | 4. Employee Personal Information backend 2. Home Page(frontend) | 2. Home page(backend) | 6. Housing (frontend) | Bug fixing